## Tracker
ID | Stage | Module | Requirement / Feature | Status | Target Date | Remarks
Phase 1: System of Record
P1-01 | Phase 1: System of Record | Data Model | Complete database structure covering all 12 data categories | Completed |  | 66 tables in 4 schemas, 11 migrations, 13 views (db/migrations)
P1-02 | Phase 1: System of Record | Data Model | User Database built from BMP's spreadsheet field list (FR-5) | Completed |  | 292/292 spreadsheet rows mapped (scripts/check_traceability.py)
P1-03 | Phase 1: System of Record | Data Model | Activity Database: tasks with steps linked back to User Database records (FR-6) | Completed |  | activity/ops schemas: template, step, dependency, data binding, evidence rule
P1-04 | Phase 1: System of Record | Data Model | Obligations defined as statutory processes (FR-1) | Completed |  | activity_template.obligation_ref + rule_definition; only one template seeded
P1-05 | Phase 1: System of Record | Data Model | Tasks defined as concrete steps with deadlines, fields and documents (FR-2) | Completed |  | step_template with deadline anchor/offset; 9 steps seeded
P1-06 | Phase 1: System of Record | Data Model | 19 Standard Lists (dropdowns) loaded | Completed |  | 19 lists, 102 values
P1-07 | Phase 1: System of Record | Data Model | Obligation status flows not started > in progress > completed / overdue | Completed |  | Task statuses + computed overdue flag (routers/activities.py)
P1-08 | Phase 1: System of Record | People & Roles | 'Don't Ask Twice': a person is entered once and reused everywhere | Completed |  | Add-to-board reuses an existing person by DIN (routers/people.py)
P1-09 | Phase 1: System of Record | People & Roles | No duplicates: people matched on DIN or PAN, companies on CIN | In Progress |  | DIN and CIN are unique; PAN is not enforced unique
P1-10 | Phase 1: System of Record | People & Roles | Similar company/person names prompt 'same entity?' instead of a duplicate | In Progress |  | GAP: not implemented in code (no fuzzy matching)
P1-11 | Phase 1: System of Record | People & Roles | Roles keep their own start/end dates so history is retained | Completed |  | directorship, directorship_role, v_director_history; overlap constraints
P1-12 | Phase 1: System of Record | Meetings | Board, AGM, EGM and committee meetings with attendance per person | Completed |  | meeting, meeting_attendance, committee tables; meetings screen
P1-13 | Phase 1: System of Record | Share Capital | Share classes, capital snapshots, allotment and transfer history | Completed |  | Holdings % calculated by v_shareholding_percent
P1-14 | Phase 1: System of Record | Filings | Government filings tracker (form, due date, filing date, SRN) | Completed |  | core.government_filing; Overdue Filings view
P1-15 | Phase 1: System of Record | Financial Records | Remuneration, loans/investments (s185/186), related-party (s188), penalties | Completed |  | Tables and generic screens in place
P1-16 | Phase 1: System of Record | Security & Privacy | Portal Access stores portal name and username only, no password | In Progress |  | Table has secret_encrypted column (write disabled by policy by default); doc says no password field
P1-17 | Phase 1: System of Record | Security & Privacy | Aadhaar numbers not stored | In Progress |  | aadhaar_encrypted column exists (write disabled by policy by default)
P1-18 | Phase 1: System of Record | Evidence | Evidence upload with durable link to task, entity or person (FR-3) | Completed |  | Upload with SHA-256 and versioning; evidence_link table
P1-19 | Phase 1: System of Record | Evidence | Required-document list defined per activity step | Completed |  | step_evidence_requirement; 4 seeded for Board Meeting
P1-20 | Phase 1: System of Record | Evidence | Document storage for evidence files (PDF, images, scans) | Completed |  | Local disk storage/ folder; the Technical Overview names MinIO
P1-21 | Phase 1: System of Record | Evidence | Database search extension for documents (pgvector) | Completed |  | document_chunk vector column + HNSW index; no embeddings loaded yet
P1-22 | Phase 1: System of Record | Rules Engine | Rules held as reviewable data with legal reference, not hard-coded | Completed |  | core.rule_definition with law_reference; is_active switch
P1-23 | Phase 1: System of Record | Rules Engine | All 37 rules loaded and evaluated per company | In Progress |  | 39 rules loaded; only 6 evaluations seeded (3 of 5 companies)
P1-24 | Phase 1: System of Record | Rules Engine | Each result shows the figures used, threshold and legal section | Completed |  | rule_evaluation.inputs; Rules screen
P1-25 | Phase 1: System of Record | Rules Engine | Rule review tracking: last reviewed date/by whom; 'pending review' until sign-off | In Progress |  | GAP: no review fields on rule_definition (reviewed_by exists only on activity templates)
P1-26 | Phase 1: System of Record | Calculated Fields | Shareholding %, director age, attendance and overdue filings calculated | Completed |  | 13 views; shown on Calculated Values screen
P1-27 | Phase 1: System of Record | Calculated Fields | Notice periods calculated | In Progress |  | Due dates computed in activity engine; no notice-period field on meetings
P1-28 | Phase 1: System of Record | Calculated Fields | Filing status calculated from the dates | In Progress |  | Overdue is computed; status itself is a typed list value
P1-29 | Phase 1: System of Record | Audit Trail | Every change recorded: who, when, value before and after | Completed |  | audit.log + audit.capture trigger; Activity Log screen
P1-30 | Phase 1: System of Record | Audit Trail | Audit trail cannot be edited or deleted | Completed |  | Update/delete/truncate blocked by triggers; tested
P1-31 | Phase 1: System of Record | Security & Privacy | Each company kept separate, enforced in database and application | Completed |  | Row-level security + API scope rules; 142 isolation tests
P1-32 | Phase 1: System of Record | Security & Privacy | Password-protected access with role-based company access | Completed |  | Sign-in, CSRF, lock-out; read/write/admin per company
P1-33 | Phase 1: System of Record | Admin Interface | Password-protected web screens to browse, search and manage all records | Completed |  | Custom FastAPI UI covers all tables (Technical Overview names SQLAdmin)
P1-34 | Phase 1: System of Record | Data Access Layer | API / data-access layer for admin, dashboard and later AI (FR-4) | Completed |  | 43 routes; docs/postman collection
P1-35 | Phase 1: System of Record | Data Seed | 5 client companies loaded | Completed |  | 5 companies seeded. Req doc: due 30 Sep 2026
P1-36 | Phase 1: System of Record | Data Seed | 5 companies fully populated: directors, shareholders, KMPs, auditors, committees, capital | In Progress |  | Seed is thin: 12 directors, 1 auditor, 1 committee in total
P1-37 | Phase 1: System of Record | Data Seed | 1 activity fully populated and correctly related (Req doc section 5) | Completed |  | Board Meeting template + one running instance with 9 tasks
P1-38 | Phase 1: System of Record | Data Seed | AGM set up: current and prior-year AGM per company with tasks and sample evidence | In Progress |  | Only 1 AGM record seeded; seeded activity is Board Meeting, not AGM
P1-39 | Phase 1: System of Record | Deployment & Ops | Web-based app for internal BMP use, portable between local and cloud (FR-15) | Completed |  | Runs on Ubuntu VM; deploy.md
P1-40 | Phase 1: System of Record | Deployment & Ops | Deployed on BMP's server (staging until hardware ready) | Completed |  | Per project status; deploy.md in repo
P1-41 | Phase 1: System of Record | Deployment & Ops | Daily backups with a copy on separate storage | In Progress |  | Procedure in deploy.md only; no backup script in repo. Confirm cron and off-server copy
P1-42 | Phase 1: System of Record | Deployment & Ops | Company separation tested explicitly before each release | Completed |  | 307 pytest tests pass (19 database + 288 web)
Phase 2: AI Assistant on one activity
P2-01 | Phase 2: AI Assistant on one activity | AI: Reading Documents | Upload a file; AI extracts fields (PDF, Word, scans) (FR-7) | In Progress |  | Stage starting; no AI code yet. Upload and storage exist
P2-02 | Phase 2: AI Assistant on one activity | AI: Reading Documents | Reviewer checks extracted details before saving; uncertain ones highlighted | In Progress |  | No code yet
P2-03 | Phase 2: AI Assistant on one activity | AI: Reading Documents | Show both values when a document conflicts with held data; never overwrite silently | In Progress |  | No code yet
P2-04 | Phase 2: AI Assistant on one activity | AI: Setting Up Work | Set up an activity (steps, deadlines, records) from a short instruction (FR-8) | In Progress |  | No prompt layer yet. ops.instantiate_activity is ready to be called
P2-05 | Phase 2: AI Assistant on one activity | AI: Notifications | AI drafts notification emails and lists recipients (FR-9) | In Progress |  | No code yet
P2-06 | Phase 2: AI Assistant on one activity | AI: Notifications | Team reviews, edits and approves; email sent through BMP's mail system | In Progress |  | No code yet. Mail system not decided (decision item 3)
P2-07 | Phase 2: AI Assistant on one activity | AI: Q&A | Answer questions from documents with a cited source (RAG) | In Progress |  | No code yet
P2-08 | Phase 2: AI Assistant on one activity | AI: Q&A | Shared reference library (Companies Act, Secretarial Standards) for all companies | In Progress |  | No code yet
P2-09 | Phase 2: AI Assistant on one activity | AI: Q&A | Client documents searched only within their own company | In Progress |  | No code yet. RLS already separates companies
P2-10 | Phase 2: AI Assistant on one activity | AI: Q&A | Document chunking and embeddings pipeline for search | In Progress |  | document_chunk table + HNSW index exist; nothing loads them
P2-11 | Phase 2: AI Assistant on one activity | AI Platform | AI tool layer (MCP server): AI acts only through permission-controlled tools | In Progress |  | No code yet. API and get_template_json endpoint exist
P2-12 | Phase 2: AI Assistant on one activity | AI Platform | LLM provider integration, switchable OpenAI / Anthropic by configuration | In Progress |  | No code yet; no LLM package in requirements.txt
P2-13 | Phase 2: AI Assistant on one activity | AI Platform | Task queue for background work (email, reading, indexing) | In Progress |  | No code yet
P2-14 | Phase 2: AI Assistant on one activity | AI Platform | Individual user accounts for everyone who approves AI actions | In Progress |  | Accounts and sign-in exist; pilot approvers not named (decision item 6)
P2-15 | Phase 2: AI Assistant on one activity | Human Confirmation | No database change or outbound message without a named person's confirmation (FR-13) | In Progress |  | Confirmation exists for task steps (ops.confirmation); not yet applied to AI actions
P2-16 | Phase 2: AI Assistant on one activity | Human Confirmation | Audit every AI-proposed action (approved/edited/rejected) and every notification sent | In Progress |  | Database audit exists for changes; nothing AI-specific yet
P2-17 | Phase 2: AI Assistant on one activity | AI Privacy | Send the AI provider only the data a task needs; no retention (FR-12) | In Progress |  | No code yet. Zero Data Retention terms are a procurement matter
P2-18 | Phase 2: AI Assistant on one activity | AI Privacy | Agreed sensitive fields withheld from the AI automatically | In Progress |  | No code yet. Field list needed (decision item 5)
P2-19 | Phase 2: AI Assistant on one activity | AI Privacy | AI tools reach only the company being worked on (FR-10) | In Progress |  | No code yet. Database-level isolation done
P2-20 | Phase 2: AI Assistant on one activity | AI Privacy | AI work history kept per company between sessions (FR-11) | In Progress |  | No code yet
P2-21 | Phase 2: AI Assistant on one activity | AI Privacy | AI provider chosen on acceptable data-retention terms | In Progress |  | Legal/procurement in progress per SOW (decision items 2 and 4)
Phase 3: Full Rollout
P3-01 | Phase 3: Full Rollout | Remaining Activities | Share allotments and transfers, EGMs, committee meetings, circular resolutions, others | Not Started |  | Data tables exist; no activity templates yet
P3-02 | Phase 3: Full Rollout | Client Portfolio | Onboard remaining client companies beyond the first 5 | Not Started |  | Req doc: progressively over 12 months. Add-company screen exists
P3-03 | Phase 3: Full Rollout | Roles & Permissions | Roles: Administrator, CS Professional and Viewer, with matching access | In Progress |  | Roles are admin/manager/client; permission tables empty. Names differ from SOW
P3-04 | Phase 3: Full Rollout | Roles & Permissions | Personal details visible only to users who need them | In Progress |  | Company access rules and people scoping exist; role-based field control not built
P3-05 | Phase 3: Full Rollout | Dashboard | Connect the supplied BMP dashboard to the live system (FR-14) | Completed |  | Built early: approved UI runs on the live API. Docs place it in Phase 3
P3-06 | Phase 3: Full Rollout | Compliance Modules | FC-GPR and FC-TRS module | In Progress |  | foreign_investment table + generic screen; no workflow
P3-07 | Phase 3: Full Rollout | Compliance Modules | ODI and ECB module | In Progress |  | odi, odi_step_down_subsidiary, ecb tables + screens; SOW lists them as out of scope for Phase 1
P3-08 | Phase 3: Full Rollout | Hosting | Hosting review: BMP server or cloud | Not Started |  | Not started
P3-09 | Phase 3: Full Rollout | Hosting | Make the application available to other organisations later (FR-15) | Not Started |  | Req doc gives no date or stage

## Summary
Stage | Total | Completed | In Progress | Not Started | % Complete
Phase 1: System of Record | 42 | 31 | 11 | 0 | 73.81%
Phase 2: AI Assistant on one activity | 21 | 0 | 21 | 0 | 0%
Phase 3: Full Rollout | 9 | 1 | 4 | 4 | 11.11%
Overall | 72 | 32 | 36 | 4 | 44.44%
Counts are formulas on the Tracker sheet and update when a Status is changed.
Stages as named in the Requirement document and the Scope of Work file (Technical Overview v1.1).

## Tech Stack
Layer | Technology | Purpose
Frontend | Jinja2 3.1 template (app/templates/dashboard.html) | One server-rendered shell page (sign-in + dashboard layout); screens are drawn in the browser
Frontend | Vanilla JavaScript ES modules (17 files) | Screens and forms driven by /api/meta; no framework, no build step
Frontend | CSS: dashboard.css (approved theme) + app.css; Bootstrap 5.3.3 (vendored) | Look and layout, served locally with no CDN
Backend | Python 3.12 (3.10+ supported) | Application language
Backend | FastAPI 0.142 + Pydantic 2 | REST API (43 routes) with metadata-driven generic record engine
Backend | Uvicorn 0.54 (scripts/run_server.py) | ASGI server
Backend | python-dotenv | Settings from .env
Database | PostgreSQL 18 | System of record: schemas core, activity, ops, audit; 66 tables, 13 views, triggers
Database | pgvector 0.8 | Vector column + HNSW index on document_chunk for AI document search (embeddings not loaded yet)
Database | btree_gist | Exclusion constraints: no overlapping periods
Database | pgcrypto | pgp_sym_encrypt for optional encrypted fields (disabled by policy)
Database | psycopg 3 + psycopg-pool | Driver and two connection pools (application login, privileged login)
Database | SQL migration files + scripts/setup_db.py | 11 migrations and 5 seed files, tracked in schema_migrations / schema_seeds
Auth & Security | Signed session cookie (Starlette SessionMiddleware, itsdangerous) | Sign-in session
Auth & Security | scrypt salted password hashes (instance/users.json) | Credential storage; database has no password column
Auth & Security | Role-based company access + PostgreSQL row-level security | read / write / admin per company; company separation in the database
Auth & Security | CSRF token header, login lock-out, CSP and security headers | Request protection
Auth & Security | HTTPS via Nginx TLS (per deploy.md; not in code) | Encrypted transport
Integrations | openpyxl 3.1 | Excel export per company (also CSV and JSON export); no Excel import found in code
Integrations | python-multipart + local file storage (storage/) | Evidence uploads with SHA-256 and versioning
Integrations | MinIO object storage (planned) | Named in Technical Overview for document storage; current build uses local disk
Integrations | Email service: BMP mail server or cloud (planned) | Notification sending in Phase 2; not decided
Testing | pytest 9 + FastAPI TestClient (httpx) | 307 tests: 19 database, 288 web; throwaway database bmp_api_test
Testing | Postman collection + environment (docs/postman) | 114 requests, 216 checks; validated with Newman
Testing | Node.js (node --check, optional) | JavaScript syntax test in the suite
Testing | scripts/check_traceability.py | Checks every spreadsheet row is mapped to a database object
Logging & Audit | audit schema: audit.log + audit.capture trigger | Immutable who / when / before / after record of every change
Logging & Audit | Python logging to stdout, collected by systemd journald (per deploy.md) | Request log with id, method, path, status, time, user
Deployment & Infra | Ubuntu VM + systemd service 'bmp' (per deploy.md) | Runs the application and restarts it on failure
Deployment & Infra | Nginx reverse proxy with TLS (per deploy.md) | Public entry point
Deployment & Infra | Nightly pg_dump backup via cron (per deploy.md; no script in repo) | Database and storage backups; off-server copy to be confirmed
Deployment & Infra | Docker (planned) | Mentioned in Technical Overview glossary; not used in the code
AI/LLM - planned | LLM API: OpenAI or Anthropic (planned) | Document reading, instruction handling, drafting; switchable by configuration; Zero Data Retention terms
AI/LLM - planned | MCP server (AI tool layer) (planned) | Permission-controlled gateway between the AI and the data
AI/LLM - planned | RAG over pgvector (planned) | Answers grounded in documents with citations
AI/LLM - planned | Redis task queue (planned) | Background work: email, document reading, indexing
AI/LLM - planned | Document parsing / OCR for PDF, Word and scans (planned) | Tool not named in the documents